## Sprint Plan
Milestone Phase | Week | Start Date | Phase Focus/parent Task | Detailed Work | Phase Deliverables | Notes
Milestone 1: Ride Module & Payment Integration (Week 1–5) | Week 1 | 4 May 2026 | Requirement Finalization & UX Planning | - Conduct requirement workshops - Finalize business rules & workflows - Define customer & driver journeys - Create UX flow diagrams (ride, driver, admin) - Identify edge cases (cancellation, no driver, retries) - Define vehicle categories (passenger-based) - Exclude Refer & Earn feature - Review shared documents & resources - Define scheduled booking timezone (St. Kitts – pending confirmation) | Approved requirements, UX flow diagrams
| Week 2 | 11 May 2026 | Figma Design (UI/UX) & System Design | - Create Figma screens - Design UI screens for Customer App - Design UI screens for Driver App - Finalize home screen (white layout selected) - Adjust black banner - Ensure UI does not mimic competitor apps (reference shared) - Review and finalize design with stakeholders - Design system architecture & DB schema | Approved Figma designs, architecture document
| Week 3 | 18 May 2026 | Backend & App Setup | - Setup backend environment & project structure - Implement authentication (login, OTP, roles) - Setup database & core APIs - Initialize mobile apps - Setup admin panel base | Working system foundation
| Week 4 | 25 May 2026 | Ride Booking Development | - Implement pickup & drop UI - Develop fare estimation logic (0–1.5 km base + per km)- Build ride booking flow - Implement ride lifecycle - Implement scheduled booking (St. Kitts timezone – subject to confirmation) - Integrate frontend with backend APIs | Functional ride booking flow
| Week 5 | 1 June 2026 | Payment Integration + Driver System (Go-Live Critical) | - Integrate payment gateway (as per shared document) - Implement payment flow (after booking, not before) - Enable payment method selection per ride - Save payment methods - Develop driver request broadcast system - Implement first-accept logic - Show driver earnings (70%) before accepting ride - Build driver app screens - Implement trip lifecycle - Implement cash payment toggle (fallback only if required) - Develop admin panel (ride & driver management) - Perform integration testing (Ride + Payment) - Deployment readiness | Core Ride System (Customer + Driver + Payment + Admin)Go-live ready system
Milestone 2: Tour Module & System Expansion (Week 6–10) | Week | Start Date | Phase Focus | Detailed Work | Phase Deliverables
| Week 6 | 8 June 2026 | Tour Module Setup | - Design Figma screens for Tour module - Create predefined tours (Half & Full Island) - Implement pricing (1–4 persons base + $30 per extra person) - Develop admin tour module - Implement tour listing UI | Tour module ready | Fixed tours only
| Week 7 | 15 June 2026 | Tour Booking & Dispatch | - Implement tour booking flow - Passenger-based pricing logic - Build dispatch panel - Enable driver assignment | Tour booking ready
| Week 8 | 22 June 2026 | Admin & Dispatch Enhancement | - Complete dispatch panel - Implement pricing configuration (if required - Reporting module (basic) - Notifications - UI optimization | Full admin system
| Week 9 | 29 June 2026 | System Testing & Stabilization | - End-to-end testing (Ride + Tour + Payment) - Bug fixes - UX improvements | Stable system
| Week 10 | 2026-07-06 | Go-Live Readiness | - Final validation - Production setup - Deployment readiness | Go-live ready system | Dependent on payment
Milestone 3: Optimization, Delivery Module & Full Platform (Week 11–14) | Week | Start Date | Phase Focus | Detailed Work | Phase Deliverables
| Week 11 | 13 July 2026 | QA & Performance Optimization | - QA testing- Fix bugs - Optimize APIs - Improve system stability | Stable system
| Week 12 | 20 July 2026 | System Optimization | - Improve performance - Reduce API usage - Implement caching - Optimize for low bandwidth | Optimized system | Mapping decision pending
| Week 13 | 27 July 2026 | Delivery Module Development | - Design delivery flow (non-food only) - Define allowed items (documents, goods) - Define use cases (small businesses) - Develop delivery APIs - Integrate delivery in apps - Test workflows - Define pricing model (zone/distance – pending) | Delivery module ready | Pricing not finalized
| Week 14 | 3 Aug 2026 | Finalization & Closure | - Optional: package photo feature (pending) - Final testing - Deployment readiness | Full platform ready

## Credentials
GoogleCloud Admin Account with Billing enabled & Credentials? | Email: Uberskb869@gmail.com Password : K@ydancer2
Domain: | Skncabs.com
Google google play developer Credentials? | Email: Uberskb869@gmail.com Password : K@ydancer2
Apple Developer Account Credentials? | Email: jermaine.mills.jm@skncabs.com Password : Topertop1$

## To be provided by the client
S .No. | Requirement
1 | Name of applications: | Customer application: SKNCabs | Driver application: SKNCabDrivers
2 | LOGOS:
3 | What is the location of your business? (Country/Cities) | St Kitts and Nevis
4 | Color code for logo/App | https://color.adobe.com/create/color-wheel | Red (#FF0A06), Yellow (#F9FF00), Black (#000000), green (#60DE2F) and White (#FFFFFF)
5 | GoogleCloud Admin Account with Billing enabled & Credentials? | Email: Uberskb869@gmail.com Password : K@ydancer2
6 | Domain: | Skncabs.com
7 | Google google play developer Credentials? | Email: Uberskb869@gmail.com Password : K@ydancer2
8 | Apple Developer Account Credentials? | Email: jermaine.mills.jm@skncabs.com Password : Topertop1$
9 | Payment Integration | Jad Cash API credentials (Live + Sandbox) + documentation | Required to implement and test payment flow (authorization & capture)
Missing Development Requirements
S .No. | Category | Missing Item | Why It’s Required
1 | Maps & Location | Google Maps API Key (or Mapbox/other) with billing enabled | Required for pickup/drop selection, route calculation, ETA, and driver navigation
2 | Domain & Security | DNS/Domain access + SSL confirmation | Needed to deploy backend APIs securely (HTTPS)
3 | App Store Compliance | Privacy Policy URL | Mandatory for both Play Store & App Store approval
|  | Terms & Conditions URL | Required for legal compliance and app publishing
4 | Authentication | OTP service decision (Firebase / SMS gateway / WhatsApp) | Needed to implement login verification flow
5 | Firebase (Recommended) | Firebase project access (or approval to create) | Required for push notifications, OTP (optional), and app analytics
6 | Push Notifications | Notification service approval (Firebase FCM) | Required for ride updates, alerts, booking status
7 | Email Service (Optional) | SMTP or email service (SendGrid, etc.) | Needed if email notifications are part of system
8 | Testing Support | Test mobile numbers / test accounts | Required for QA and UAT testing
9 | Deployment Access | Server region confirmation (India / Middle East etc.) | Impacts latency and compliance
10 | Backup & Security (Optional) | Backup preference / policy approval | Important for production data safety
11 | App Store Setup | App bundle ID / package name approval | Required before building apps for store submission
12 | App Store Content (Later Stage) | App descriptions (short & long) | Required during publishing phase
|  | Initial screenshots reference | Helps prepare store listing (final can be generated later)
13 | Data Migration (If applicable) | Confirmation if old data needs to be migrated | Impacts backend planning and timelines

## MOM
Date | MOM
2026-04-05 | Please find below the Minutes of Meeting (MoM) for the Project Kickoff discussion: Project: SKN Cabs Platform (Ride, Tour, and Delivery System) Type of Meeting: Project Kickoff Date: 04/05/2026 Mode: Virtual / Online
Attendees Kayla (Client Representative) Gaurav (Development Team) Vishal (Development Team) Namita (Development Team) Pragyan (Development Team)
Agenda of the Meeting Cash payment option discussion Refer & Earn feature requirement Vehicle category structure Ride booking and payment flow Tour package structure Delivery module scope Fare calculation logic Driver commission structure Payment integration discussion Mapping (Waze) requirement Milestones and project updates Access to shared resources
Objective of the Meeting To align on the functional requirements and system flow for the SKN Cabs platform including ride, tour, and delivery modules, and to clarify payment, integration, and execution approach before development. Key Discussion Points 1. Cash Payment Cash payment option exists in the system as a toggle. It is not normally used in production. It was previously enabled temporarily during payment gateway issues. Cash option can remain only if toggle support is available; otherwise, it should not be included. 2. Refer & Earn Feature already exists in the system for more than 2 years. Usage is very low due to small reward value. Client confirmed it is not required. 3. Vehicle Categories Categories are based on passenger capacity, not vehicle type. Backend supports creation of categories. Discussed categories: 1–4 persons 5–10 persons Luxury (1–6 persons mentioned) 4. Ride Booking and Payment Flow User selects pickup and drop location. System shows fare before booking confirmation. Booking is confirmed after fare display. Payment method (card/wallet) is added after booking process starts. Payment method is saved for future use and selected per booking. 5. Tour Module Fixed tour packages only. Tours: Half Island Tour Full Island Tour Pricing: Base price for 1–4 persons Additional $30 per extra person 6. Delivery Module Only non-food delivery is included. Target users are small businesses. Allowed items: Documents, cosmetics, jewelry, flowers, small goods Not allowed: Food delivery 7. Delivery Workflow Discussion Photo at pickup and delivery was discussed. Not finalized. 8. Fare Calculation Ride fare is distance-based. Base fare applies for initial distance (0–1.5 km). After that, per km charges apply. Delivery pricing is not finalized (distance vs zone-based discussed). 9. Driver Commission Driver receives 70% of fare. Platform receives 30%. Driver sees earnings before accepting ride. 10. Payment Integration (IMPORTANT) Payment gateway document has been shared. Team has reviewed it internally. Final confirmation is pending with developer before implementation. Important Note: Payment integration is a critical dependency and the system cannot go live without it. 11. Mapping (Waze) Client asked about Waze integration. Requirement is not finalized. 12. Project Updates & Communication Updates will be shared twice weekly: Start of week End of week Mid-week meetings may be arranged if required. Communication via WhatsApp. 13. Milestones Existing milestone structure will be revised due to updated scope. Ride, Tour, and Delivery modules will be included in updated milestones. 14. Access & Documentation Shared drive access has been provided. All documents have been downloaded successfully. No access issues reported.
Action Items Confirm cash payment toggle requirement Confirm delivery pricing model Confirm Waze integration requirement Confirm delivery photo verification feature Finalize payment gateway integration with developer Update milestone structure as per revised scope
Next Steps Developer to finalize payment integration approach Technical evaluation for mapping system Clarify delivery pricing model Update milestones and project plan Continue weekly updates as agreed Additional Notes Refer & Earn feature is not required. Food delivery is excluded from the system. Payment integration is mandatory for go-live. System includes Ride, Tour, and Delivery modules.

## Feedback
Task | Feedback | Date | Status